# CASCADIA LIQUOR — 'THE DEN REWARDS' LAUNCH MARKETING & COMMUNICATIONS PLAN

## 1. Summary

Objective: Introduce The Den Rewards — Cascadia’s new loyalty program designed to increase repeat visits, build guest loyalty, and grow sales.

Launch Timeline: 8-week phased campaign   (Awareness → Enrollment → Engagement → Retention).

## 2. Marketing Communication Overview

A. Internal Communications

| Audience | Channel | Timing | Message / Goal |
| --- | --- | --- | --- |
| Store Managers | Teams briefing + toolkit | Week -2 | Overview of rollout, expectations, FAQs |
| Leadership / Exec | Weekly KPI email | Weekly | Enrollment + campaign performance |

B. External Communications

| Week | Phase | Focus | Key Activities |
| --- | --- | --- | --- |
| (-1–2) | Teaser and Early Sign-Up | Pre-Launch incentive | Bonus points – Newsletter, socials, tv |
| 3–4 | Launch | Introduce the Den | Meta/Google/contest/transit/instore/News Release etc. Contest/Points Bonus |
| 5–6 | Engagement | Build habit | 2x Points Tuesday, Local Producer Bonus – socials/MMS, & ongoing campaigns |

| ## 3. Channel Marketing Tiers |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## CHANNEL | ## MONTHLY COSTS | ## MODERATE | ## COMPREHENSIVE | ## KPIs |
| ## META | ## $300 | ## $800 | ## $800 | ## Signups |
| ## Google | ## $1600 - $2500 | ## $3000 | ## $4100 | ## Conversion, CPC |
| ## Canada Post | ## $3000/store | ## - | ## - | ## QR Scan Rate |
| ## Radio | ## $1200/week | ## $2400 (2 weeks) | ## $4800 (4 weeks) | ## Reach, Recall |
| ## Print/Vic Buzz | ## $2000/pg/contest | ## $5000 | ## $7000 | ## Reach, Awareness, Entries |
| ## Transit | ## $6000/mos | ## $6000 (4 wks) | ## $6,000 (4 wks) | ## Impressions |
| ## In Store Collateral | ## $8,000 | ## $8,000 | ## $10,000 | ## Signups per store |
| ## Buttons | ## $300 | ## $300 | ## $300 | ## Awareness, signups at till |
| ## Email/SMS | ## $0 | ## $0 | ## $0 | ## Open and click rates |
| ## Socials | ## $0 | ## $0 | ## $0 | ## Engagement, Reach |
| ## TV Screens | ## $0 | ## $0 | ## $0 | ## Impressions |
| ## Save on Foods Ads | ## $0 | ## $0 | ## $0 | ## Impressions |
| ## Ticker Ad on CHEK | ## $0 | ## $0 | ## $0 | ## Impressions |
| ## TOTALS |  | ## $34,000 (1.64%) | ## $47,500 (1.72%) | ## % = uplift in sales needed to break even |

## 4. Creative & Messaging Framework

• Program name and visual identity - The Den Rewards/ The Den VIP Rewards
• Core tagline: Welcome to the Den, Join the Den Family
• Tier visuals and micro-taglines: Cub / Brown Bear / Grizzly

• Point Names:  Den Points

## 5. Measurement & Reporting

| KPI | Target | Checkpoint |
| --- | --- | --- |
| Initial Enrollment rate | 25 – 30,000 contacts yr. 1 | Monthly dashboard |
| Repeat visits (members) | +20% vs baseline | Post-Week 8 analysis |
| POS accuracy | ≥ 99.5% | Daily report |
| Guest satisfaction | ≥ 70% favorable | Pulse survey Week 8 |

## 6. Appendices (TBD)

• Press release draft  - Times Colonist, One Publishing, Business Examiner, Local Newspapers, Local Radio Stations
• Staff FAQ and talking points – on website and email to stores
• Store signage mockups – we’ll create these once finalized on creative theme
• Draft emails and newsletter creative – for approval